## About
ABOUT THIS GANTT CHART
Visualize and track your projects using this Gantt chart template. To start, enter the tasks you're working on in the Milestone Description section and then enter details for each task. The data will automatically update and it’s easy to insert new tasks or use the scrollbar to scroll through the timeline.
• Use Progress to add how much of the project you finished by adding a percentage number. • Add the day you started your project in the Start Date. • Finish your calculations by filling in the number of days you need to complete your project in the No. of Days field.

## Light
Assignment Website
Goku |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Aidan Willis
Project Start Date: | 2023-05-17 |  |  |  |  | May | [20 empty] | June | [27 empty] | July
Scrolling Increment: | 0 | time axis 2023-05-17 to 2023-07-11
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2023-05-17 to 2023-07-11
Interface Design
Create Layout | Low Risk | Sven Hoerler | 25% | 2023-05-17 | 3
Graphic Design options | Med Risk | Rob McNaught | 15% | 2023-05-20 | 5
Development Options | High Risk | James Sadler | 50% | 2023-05-25 | 4
Make Schedule | Milestone | Aidan Willis | 40% | 2023-06-02 | 1 | bar: 2023-06-02
Colours | On Track | Rob McNaught | 90% | 2023-05-29 | 4
Usability
Understanding Accessibility | High Risk | James Sadler | 60% | 2023-06-03 | 9
Implementation | On Track | James Sadler | 50% | 2023-06-12 | 4
Finalize any accessibility criteria | Milestone | James Sadler | 33% | 2023-06-16 | 1 | bar: 2023-06-16
Completion of interface with accessibility options | Goal | Sven Hoerler | 40% | 2023-06-17 | 1 | 2023-06-17: 2
Make sure it is efficient and fast to use | Med Risk | Aidan Willis | 23% | 2023-06-18 | 5
Resources
Find resource and labour costs | High Risk | Gilbert Roy-Gapper | 45% | 2023-06-23 | 4
Find Alternatives to high cost items | On Track | Gilbert Roy-Gapper | 12% | 2023-06-27 | 10
Implement any alternatives over current items | On Track | James Sadler | 18% | 2023-07-07 | 6
Make sure the alternative items work with the stakeholders | Goal | Aidan Willis | 80% | 2023-07-13 | 1
Fix any efficiency errors | Low Risk | James Sadler | 20% | 2023-07-14 | 9
Documentation
Make sure there is a github repository | High Risk | Aidan Willis | 90% | 2023-07-23 | 5
Make sure all programmers can push to the repository | On Track | Aidan Willis | 50% | 2023-07-28 | 5
Create a wiki for use of the repository | Med Risk | Aidan Willis | 40% | 2023-08-02 | 7
Release deployents for the application | High Risk | James Sadler | 20% | 2023-08-09 | 4
Iteration 2 complete | Milestone | James Sadler | 40% | 2023-08-13 | 1
END OF FILE
To add more data, Insert new rows ABOVE this one

## Dark
PROJECT TITLE
Goku |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Aidan Willis
Project Start Date: | 2023-05-17 |  |  |  |  | May | [13 empty] | June | [34 empty] | July
Scrolling Increment: | 1 | time axis 2023-05-18 to 2023-07-12
Milestone description | Category | Assigned to | Progress | Start | Days | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W
Interface Design
Create Layout | Low Risk | Sven Hoerler | 25% | 2023-05-17 | 3
Graphic Design options | Med Risk | Rob McNaught | 15% | 2023-05-20 | 5
Development Options | High Risk | James Sadler | 50% | 2023-05-25 | 4
Make Schedule | Milestone | Aidan Willis | 40% | 2023-06-02 | 1 | bar: F
Colours | On Track | Rob McNaught | 90% | 2023-05-29 | 4
Usability
Understanding Accessibility | High Risk | James Sadler | 60% | 2023-06-03 | 9
Implementation | On Track | James Sadler | 50% | 2023-06-12 | 4
Finalize any accessibility criteria | Milestone | James Sadler | 33% | 2023-06-16 | 1 | bar: F
Completion of interface with accessibility options | Goal | Sven Hoerler | 40% | 2023-06-17 | 1 | S: 2
Make sure it is efficient and fast to use | Med Risk | Aidan Willis | 23% | 2023-06-18 | 5
Resources
Find resource and labour costs | High Risk | Gilbert Roy-Gapper | 45% | 2023-06-23 | 4
Find Alternatives to high cost items | On Track | Gilbert Roy-Gapper | 12% | 2023-06-27 | 10
Implement any alternatives over current items | On Track | James Sadler | 18% | 2023-07-07 | 6
Make sure the alternative items work with the stakeholders | Goal | Aidan Willis | 80% | 2023-07-13 | 1
Fix any efficiency errors | Low Risk | James Sadler | 20% | 2023-07-14 | 9
Documentation
Make sure there is a github repository | High Risk | Aidan Willis | 90% | 2023-07-23 | 5
Make sure all programmers can push to the repository | On Track | Aidan Willis | 50% | 2023-07-28 | 5
Create a wiki for use of the repository | Med Risk | Aidan Willis | 40% | 2023-08-02 | 7
Release deployents for the application | High Risk | James Sadler | 20% | 2023-08-09 | 4
END OF FILE
To add more data, Insert new rows ABOVE this one

## Color
PROJECT TITLE
Goku |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Aidan Willis
Project Start Date: | 2023-05-17 |  |  |  |  | May | [13 empty] | June | [27 empty] | July
Scrolling Increment: | 5 | time axis 2023-05-22 to 2023-07-16
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2023-05-22 to 2023-07-16
Interface Design
Create Layout | Low Risk | Sven Hoerler | 25% | 2023-05-17 | 3
Graphic Design options | Med Risk | Rob McNaught | 15% | 2023-05-20 | 5
Development Options | High Risk | James Sadler | 50% | 2023-05-25 | 4
Make Schedule | Milestone | Aidan Willis | 40% | 2023-06-02 | 1 | bar: 2023-06-02
Colours | On Track | Rob McNaught | 90% | 2023-05-29 | 4
Usability
Understanding Accessibility | High Risk | James Sadler | 60% | 2023-06-03 | 9
Implementation | On Track | James Sadler | 50% | 2023-06-12 | 4
Finalize any accessibility criteria | Milestone | James Sadler | 33% | 2023-06-16 | 1 | bar: 2023-06-16
Completion of interface with accessibility options | Goal | Sven Hoerler | 40% | 2023-06-17 | 1 | 2023-06-17: 2
Make sure it is efficient and fast to use | Med Risk | Aidan Willis | 23% | 2023-06-18 | 5
Resources
Find resource and labour costs | High Risk | Gilbert Roy-Gapper | 45% | 2023-06-23 | 4
Find Alternatives to high cost items | On Track | Gilbert Roy-Gapper | 12% | 2023-06-27 | 10
Implement any alternatives over current items | On Track | James Sadler | 18% | 2023-07-07 | 6
Make sure the alternative items work with the stakeholders | Goal | Aidan Willis | 80% | 2023-07-13 | 1 | 2023-07-13: 2
Fix any efficiency errors | Low Risk | James Sadler | 20% | 2023-07-14 | 9
Documentation
Make sure there is a github repository | High Risk | Aidan Willis | 90% | 2023-07-23 | 5
Make sure all programmers can push to the repository | On Track | Aidan Willis | 50% | 2023-07-28 | 5
Create a wiki for use of the repository | Med Risk | Aidan Willis | 40% | 2023-08-02 | 7
Release deployents for the application | High Risk | James Sadler | 20% | 2023-08-09 | 4
END OF FILE
To add more data, Insert new rows ABOVE this one